## Sheet1
| Month | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  | 2024-05-01
Feature |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Login Feature - Front End | bar: 2023-08-01 Week 1 to 2023-08-01 Week 2
Login Feature - Back End | bar: 2023-08-01 Week 1 to 2023-08-01 Week 2
Dashboard- Front End | bar: 2023-08-01 Week 3 to 2023-09-01 Week 1
Dashboard- Back End | bar: 2023-08-01 Week 3 to 2023-08-01 Week 4
Calendar - Front End | bar: 2023-09-01 Week 1 to 2023-09-01 Week 3
Calendar - Back End | bar: 2023-09-01 Week 1 to 2023-09-01 Week 2
Course/Module Page - Front End | bar: 2023-11-01 Week 3 to 2023-12-01 Week 4
Course/Module Page - Back End | bar: 2023-11-01 Week 2 to 2023-12-01 Week 2
Personal Particulars - Front End | bar: 2023-10-01 Week 2 to 2023-10-01 Week 3
Personal Particulars - Back End | bar: 2023-10-01 Week 2 to 2023-10-01 Week 3
Document Content Handler - Front End | bar: 2023-09-01 Week 4 to 2023-10-01 Week 1
Document Content Handler - Back End | bar: 2023-09-01 Week 3 to 2023-10-01 Week 1
Course Administrator Access - Front End | bar: 2023-10-01 Week 4 to 2023-11-01 Week 2
Course Administrator Access - Back End | bar: 2023-10-01 Week 4 to 2023-11-01 Week 1
Pilot Testing | bar: 2024-01-01 Week 2 to 2024-02-01 Week 1
Regression Testing | bar: 2024-02-01 Week 2 to 2024-03-01 Week 2
System Integration Test (Back End) | bar: 2023-12-01 Week 3 to 2024-01-01 Week 1
Back End Team
Front End Team
Testers